## Sheet2
Phase 1: Early Design
Task | Subtasks | Assigned Member(s) | Expected Deliverables
Introduction | - Research project goals | all members | - Documented goals
| - Write project scope and objectives |  | - Overview presentation
- Create presentation overview
Phase 2: Hardware Components
Task | Subtasks | Assigned Member(s) | Expected Deliverables
Raspberry Pi Setup | 1. Install OS: | Devang | - Functional Raspberry Pi
| - Install Raspberry Pi OS |  | - ROS2 installed
| 2. ROS2 Installation: |  | - Verified connectivity
- Install ROS2 Humble
3. Connectivity Test:
- Test SSH and sensor connections
Power System | 1. Battery Configuration: | Devang | - Stable power delivery
| - Verify battery voltage and connections |  | - Documented setup
2. Power Distribution:
- Test power distribution to components
Motors & Driver | 1. Motor Testing: | Devang | - Functional motors
| - Test DC motors individually |  | - Documented driver and motor connections
2. Driver Setup:
- Connect motor driver (ZK-BM1) to motors and Raspberry Pi
3. Servo Control:
- Test servo motor
LIDAR & Camera | 1. LIDAR Testing: | Fazil | - Functional LIDAR and camera
| - Connect and test LIDAR module |  | - Test data recorded
2. Camera Setup:
- Test Raspberry Pi camera or USB camera
Color sensors for steering | lego gear setup for higher gearing ratio, external support to the mechanism for proper movement, placement of color sensor | Vinay
Color sensors for odom |  | Devang, Vinay
Phase 3: Assembly
Task | Subtasks | Assigned Member(s) | Expected Deliverables
Chassis Fabrication | 1. Chassis Build: | All members | - Assembled chassis
| - Assemble or fabricate chassis based on CAD |  | - Mounted components
2. Component Mounts:
- Mount motors, sensors, Raspberry Pi, and driver
Integration Testing | 1. Hardware Check: | Devang, Vinay, Aditya , Fazil | - Stable assembly
| - Verify all hardware components are securely connected |  | - Initial test results
2. Power Test:
- Test power distribution to all components
Phase 4: ROS2 and Packages
Task | Subtasks | Assigned Member(s) | Expected Deliverables
Steering & Control | 1. Teleoperation: | Fazil, Aditya | - Functional teleop node
| - Write basic teleop node |  | - Steering test results
2. Steering Test:
- Test servo and motor control via ROS2
Mapping & Localization | 1. SLAM Setup: | Fazil | - Functional SLAM
| - Install SLAM packages |  | - Sensor fusion results
2. Sensor Fusion:
Fuse LIDAR and IMU , ODOM data for localization
Navigation | 1. Nav2 Installation: | Aditya | - Working navigation stack
| - Install and configure Nav2 stack |  | - Path planning test results
2. Path Planning:
- Test global and local planners in simulation
Advanced Features | 1. Object Tracking: |  | - Object tracking prototype
| - Implement basic object detection using the camera |  | - Enhanced teleop functionality
2. Advanced Teleop:
- Add advanced teleoperation controls
Bot_Description | 1. Create TF Frames: | Aditya, Vinay
- Define transforms between robot components
2. Write URDF/Xacro:
- Write URDF file for robot description
- Add parameters for robot dimensions
3. Visualize in RViz:
- Verify the robot model and transforms in RViz
- Verified TF tree
- Complete URDF/Xacro file
- Robot model visualized in RViz
Hardware_Interface_ROS2_Control | 1. Develop Mock Hardware Interface: | Aditya
- Write mock code to simulate hardware
2. Setup ROS2 Control Components:
- Configure robot controllers for motors
ROS2 | 1. Setup Workspace: | All members
- Configure ROS2 workspace
2. Develop Nodes:
- Write ROS2 nodes for publishing velocity commands
- Create nodes for reading sensor data
3. Integration:
- Integrate hardware and software for basic robot motion
Fazil, Aditya
- Functional ROS2 workspace
- Working ROS2 nodes for motion and sensor input
Simulation | 1. Gazebo Setup: | Fazil, Vinay
- Create a simulation environment in Gazebo
2. URDF Integration:
- Load the URDF into Gazebo
3. Test Navigation:
- Test robot’s motion and path planning in simulation
- Simulation environment with functional robot
- Logs of simulation test results
PID Control | 1. Implement PID Control: | Vinay | - Optimized PID parameters
| - Write a PID controller for velocity and steering |  | - Logs of simulation and hardware test results
2. Test in Simulation:
- Test and tune PID parameters on TurtleBot simulation
3. Test on Hardware:
- Apply PID control on real robot and optimize parameters
| Subtasks | Assigned Member(s) | Expected Deliverables
System Overview | - Write detailed documentation of hardware, software, and system architecture | Rotational | - Comprehensive documentation
User Guide | - Develop step-by-step guides for setup and testing | Rotational | - User-friendly guides
Reports | - Prepare weekly progress reports and a final project presentation | Rotational | - Reports and presentations